## SD Experiences
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2018
Strategic Direction: Enhance Experiences Establish a welcoming space where the community enjoys enriched experiences
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Establish programming that aligns with organizational values and strategic directions | Create a programming plan template that includes space to document at least 2 measurable outcomes and goals | AS Programming Team, YS Staff, Supervisors | Q4 2017 | Q3 2018 | Completed | Staff have completed the programming plan templates for the Adult and Youth Services departments; the AS staff will officially launch the plan in early 2019 and review the survey results and patron feedback on an ongoing basis; the YS staff are updating their plan to ensure it continues to align with 21st Century Skills across all age groups
| Annually review 30% of programs, measuring the outcomes listed in the program plan using patron surveys | AS Programming Team, YS Staff, Supervisors | Q4 2017 | ongoing | In Progress | YS Staff and the AS Programming Team will conduct the first annual review during Q4 2018
Goal 2: Review and refresh Library collections | Assess current print holdings, review usage statistics, and refresh 20% of the collection annually | Supervisors | Q1 2018 | ongoing | Completed-Ongoing | Weeded/refreshed Juv NF, Juv Fic, YA NF, Picture Books, M-Z Adult Fic, Large Print, DVDs, CDs, BkCD in 2017; equals 33.7% of total collection; received $7500 Bilingual Books Grant from State Library in FY16/17 & FY17/18 to refresh the juvenile Foreign Languages Collection
| Review and update collection development policy | Supervisors | Q4 2017 | Q4 2018 | Completed | Draft updated by supervisors August 2017; reviewed by staff September 2017; finalized & posted January 2018
Goal 3: Review online resources | Assess current online resources and review usage statistics at the end of each fiscal year, cancelling services that show a decrease in use of 10% or more from the prior year | Library Manager, AS Librarian | Q3 2017 | ongoing | Completed-Ongoing | Canceled Gale Courses, Novelist, Newsbank, and Pronunciator due to low usage; Gale Courses ($5556) usage from FY15/16 to 16/17 50% decrease; Novelist ($2142) 39% decrease; Newsbank ($2235) 42% decrease; Pronunciator ($830) 80% decrease
| Ensure staff are familiar with online resources by providing trainings and updates every two months, resulting in 100% of staff having minimum knowledge of available online resources by 2021 | Clerks | Q1 2018 | Q2 2021 | Completed | Supervisors encourage staff to use Learning Hours to continuously update themselves on the online resources; staff have provided presentations at the two Staff Learning Summits on a variety of online resources to ensure all staff know what is available for our patrons
| Create and implement marketing plan for online resources with at least 3 strategies and evaluate the usage statistics annually | Library Manager | Q1 2018 | Q2 2018 | Completed | Starting January 2018: regular posts on social media, creating handouts, and introducing Tech Pop ups (ex. Tech Pop Up on Libby ebook app January 2018); providing app overview & tech classes at local senior facilities during outreach
Goal 4: Evaluate physical space and make recommendations to create a more welcoming environment | Assess library space and layout with current and future use in mind by surveying staff and patrons every two years, with a minimum of 50 respondents made up of various stakeholders | Supervisors | Q2 2018 | ongoing | In Progress | Using survey data from the Strategic Planning process in late 2016 as a base, staff is currently working on a space use survey focused on the Adult Services Area; will launch the survey after a statistical pilot project is completed in January 2019 which will include hourly head counts for a better sense of how and when the library is used by the community
| Track current usage to determine need and then establish defined spaces for learning, technology, group study, and community use | Supervisors | Q2 2018 | Q2 2020 | Waiting | Will revisit once the Library Park Redesign is completed so staff can incorporate new indoor/outdoor spaces
| Identify at least 3 resources and/or individuals that can assist with space reorganization | Supervisors | Q1 2018 | Q3 2018 | Completed | Undisclosable, ABHE (Library Park redesign), and Linda Demmers/Libris DESIGN (a good resource of information)
Goal 5: Review options for expanding the indoor/outdoor space of the Library | Conduct community meeting to gather input and then work with the City to develop ideas for how best to utilize park space for the Library | Library Manager | Q2 2018 | Q2 2019 | In Progress | City staff met with ABHE for Library Park Redesign Fall 2017; met with Foundation June 2018; presented preliminary plans to Library Board July 2018 as well as the City Council and Friends in October 2018
| Assess community need and review best practices for a Café experience at the Library by visiting a minimum of four local library cafes by 2022 | Café Project Team | Q2 2020 | Q2 2022 | Waiting
| If a Café is feasible, work with the City to review legal and policy issues, and identify up to 3 potential locations as well as 3-5 potential partners | Café Project Team | Q2 2020 | Q2 2022 | Waiting
Goal 6: Support lifelong learning, with an emphasis on 21st Century skills for youth and "Active Mind, Active Life" programming for seniors | Refresh current programming with a minimum of 20% of programming having an emphasis on 21st Century skills by 2021 | AS Programming Team, YS Staff | Q1 2018 | Q3 2021 | Completed | Staff started STEAM programming with Makerspace equipment funded by the Foundation in 2017; Youth Librarians received the Innovation Station Grant from the State Library in December 2017 and partnered with Oak Crest Institute of Science to purchase telescopes, circuitry kits, and other items that were used during Spring Break for their SciLab programs; after the success of SciLab in April 2018, the program has been expanded for the summer reading program; for FY17/18, there have been 88 STEAM programs for youth, which comprises 30.8% of total youth programming for that period; STEAM programming continues in FY18/19
| Partner with the school district and other educational organizations within the community to expand the offerings and promotion of youth programming with staff attending 2-4 school or PTA meetings per year | YS Staff | Q2 2018 | ongoing | Completed-Ongoing | Staff has partnered with Monrovia Reads and MUSD on the Monrovia Reads Van project; attended the annual Santa Fe Parent Literacy Night October 2017; staff attends monthly Healing Connections meetings at the high school; hosts monthly meetings for local school librarians in the Library's Heritage Room
| Review current programming for seniors and identify areas where new or refreshed ideas are needed, implement 3-5 programs and/or services with measurable outcomes by 2019 | AS Supervisor, AS Librarian | Q1 2018 | Q3 2019 | In Progress | Staff provide monthly visits to local senior facilities and a survey of their residents has resulted in new ideas for programs like Classic Movie Afternoon, that was introduced September 2018; staff have provided modified library programs to local facilities, including a currents event program on voting, a training for seniors on using Lyft, and workshops on ebooks; staff is planning a book club for residents that will be coming soon
| Identify and meet with potential community organizations that cater to seniors in the community resulting in 3-5 visits by library staff by 2019 | AS Supervisor, AS Librarian | Q2 2018 | Q1 2019 | Completed | Staff has partnered with the Community Center's Senior Group for Senior Lunch & Learn visits; provided presentations on library services and a roving collection to both the Senior Group and local facilities; regularly partners with Brookdale, Regency, and Heritage Park; presented on volunteer opportunities for Older Adults at Providers Group meetings; staff visits each local senior facility monthly
| Implement new or expanded senior programming and regularly review it's impact based on feedback from the community and measurement of outcomes using surveys with a minimum of 10% of program attendees responding | AS Supervisor, AS Librarian | Q4 2018 | Q3 2019 | Completed-Ongoing | Staff began providing scaled down versions of library programs at local facilities for seniors, including a DIY Garden Workshop in April 2017 and Hawaiian dance demo in August 2018; provided surveys in Summer 2018 for Older Adults and launched new programming in September 2018 in response to requests, including a monthly Classic Movie Series

## SD Access
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2018
Strategic Direction: Enhance Access Expand opportunities for the community to access the Library and its resources
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Evaluate and recommend Library hours of operation to meet the needs of the community | Review information received from community and assess staffing levels and resource allocation needed by Q4 2018 | Circulation Supervisor, Library Manager | Q4 2017 | Q4 2018 Q1 2019 | In Progress | Reviewed survey results; supervisors meeting to assess staffing levels needed; waiting for completion of statistical pilot project from November 2018-January 2019 that will provide more complete data on how and when the library is used by incorporating hourly head counts into the public desk statistics forms
| If a change in hours is made, market and promote new operating schedule to the community resulting in an increase of library visits by 10% within the first year of the new schedule being implemented | Circulation Supervisor, Library Manager | Q2 2019 | Q3 2021 | Waiting
Goal 2: Evaluate and recommend Library needs in Southern Monrovia | Conduct a random survey of the community with a minimum of 50 respondents from Southern Monrovia and review information received to assess needed services | YS Staff, Supervisors | Q1 2018 | Q2 2020 | In Progress | Had 22 survey respondents when the Monrovia Reads Van visited Plymouth Elementary May 2018; will also incorporate surveys into programs at Station Square and other S. Monrovia locations in FY18/19
| Assess staffing levels and existing budget and explore redeploying existing resources if new or expanded services are needed with a minimum of two new and/or expanded services launched by 2021 | Supervisors | Q1 2018 | Q4 2021 | Completed-In Progress | Monrovia Reads Van launched March 2018, servicing Plymouth Elementary; Summer Reading Kickoff June 2018 was held at Station Square with 202 in attendance; during Summer 2018, the Monrovia Reads Van visited the Huntington Oaks Shopping Center on a monthly basis; from August-October 2018 the Van had 1094 visits, checked out 497 items, and renewed or created 62 library cards while visiting the local elementary schools
| If new or expanded services are created, establish a marketing plan and promote new services to Southern Monrovia resulting in a minimum increase in use/visits by 10% after two years | Supervisors | Q1 2018 | Q2 2022 | In Progress | Public Relations Team held its first meeting in September 2018
Goal 3: Evaluate and recommend ways to enhance the mobility of the Library | Review best practices for providing mobile services and identify three potential locations for hosting outreach with community partners, holding at least 4 meetings with partners by 2020 | Supervisors | Q1 2018 | Q2 2020 | Completed | Using the Monrovia Reads Van, a collaboration with community partners: Monrovia Reads, the Library Foundation, Foothill Credit Union, and other corporate sponsors, staff have engaged in outreach at the local elementary schools, participated in the MAP Block Party and Spring Egg Hunt in March 2018, the MAP Neighborhood Conference in April 2018 at Monrovia High School and MAP Block Parties during the summer; the Monrovia Reads Van was at the Mayflower Family Fun Night in April 2018 and the Foothill Unity Back to School annual event in August 2018; staff attends monthly Monrovia Reads meetings and met with MUSD staff 3 times for the Monrovia Reads Van as well as hosting monthly meetings with MUSD school librarians at the Library
| If new mobile services are created, establish a minimum of 3 outcomes and at least 5 goals to measure effectiveness, including an annual report for the Library Board's review | Supervisors | Q2 2018 | Q4 2020 | Completed | Staff drafted a plan with 3 outcomes and 5 goals and reviewed it with the Mobile Library Services Team; have incorporated the plan into the activities and directions for the 18/19 school year; outcomes will be included in the annual Monrovia Reads Van report to the Library Board
| If new or expanded mobile services are created, design a marketing plan and promote new services to community resulting in a 10% increase in use and/or program attendence after second year | Supervisors | Q2 2018 | Q2 2022 | In Progress | Public Relations Team will meet with the Mobile Library Service Team to devise a marketing plan; promotional materials were created for the launch and will be expanded for the first full year of service, the 18/19 school year; the second year of service is the 19/20 school year which means staff will review attendance numbers for the 20/21 school year to evaluate impact of marketing and promotion of the program

## SD Partnerships
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2018
Strategic Direction: Enhance Partnerships Establish strategic partnerships and increase community engagement
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Develop partnership with social services providers | Identify 3-5 potential community and City partners and establish strategic networks of support | AS Staff | Q2 2020 | Q3 2021 | In Progress | Staff has identified Foothill Workforce Development Board (FWDB), Foothill Unity Center, Dementia-Friendly Monrovia (DFM), and LA County Dept. of Mental Health (LAC-DMH) as potential partners and networks of support; the library partnered with LAC-DMH on a wellness fair in 2017 & staff training in August 2018; staff attends DFM meetings and attended the Foothill Unity Back to School event in 2018; staff partnered with FWDB on job skills training for Veterans and a workshop for English language learners attended by Literacy staff October 2018
| Review information received from community and assess best practices for providing social services by contacting/visiting 3-5 local libraries or social service agencies by 2021 | AS Staff | Q4 2020 | Q2 2021 | In Progress | Staff will visit Azusa, Glendale, and Pasadena public libraries to learn more about their partnerships with local social service agencies in 2019
| Evaluated 100% of the currently offered social services within the Library for any duplication of effort and ensure the maximum effectiveness of Library staff and resources | AS Staff | Q4 2020 | Q2 2021 | Waiting
| If new or additional services are needed, promote to community and targeted populations most in need, and then measure ongoing effectiveness with a survey that has at least 20 respondents one year after new service is launched | AS Programming Team, YS Staff, Supervisors | Q4 2021 | Q4 2022 | Waiting
Goal 2: Develop and expand partnership with MUSD regarding Literacy, Veterans, and Youth Services | Meet with MUSD staff, including school librarians, teachers, and principals, to assess current partnership and discuss ongoing and future needs as related to Literacy, Veterans, and Youth Services | Supervisors, Literacy Coordinator, AS Librarian | Q4 2018 | Q2 2022 | Completed-In Progress | Staff met with MUSD 3 times from August 2017 through February 2018 regarding the Monrovia Reads Mobile Literacy Program; the Library hosts the school librarians' monthly meeting in the Heritage Room; the Literacy Coordinator offers regular tours to students at the Adult School as well as hosting classes and leading workshops on the Adult School campus
| Draft action plan with 3-5 outcomes and 5-7 goals to measure the impact of expanded partnership and related activities | Supervisors, Literacy Coordinator, AS Librarian | Q2 2019 | Q4 2022 | Waiting | Will incorporate elements of the Mobile Literacy Van outcomes and goals into the action plan
| Evaluate best practices regarding sustaining partnerships and regularly review needs to keep partnership healthy and effective by meeting with staff at three local libraries with social service partnerships by 2022 | Supervisors, Literacy Coordinator, AS Librarian | Q4 2018 | Q2 2022 | In Progress | Oct. 2018 Remove Goal Activity, similar in wording to second activity under Goal 1: Review information received from community and assess best practices for providing social services by contacting/visting 3-5 local libraries or social service agencies by 2021
Goal 3: Develop and expand partnership with local historical organizations and related City departments | Meet with local historical organizations 3-5 times per year over the next three years to assess current partnerships and discuss ongoing and future needs in preserving the City's rich heritage and local history resources | Library Manager, AS Supervisor | Q2 2017 | Q4 2020 | Completed-In Progress | Staff held meetings with Legacy Project and Museum; purchased PastPerfect software December 2017 for historical collections; launched the website for the Legacy Project's historical online collection in May 2018 & holding places for future online collections from the Museum and Library
| Promote historical research opportunities and resources available at the Library resulting in a 15% increase in the use of historical materials by 2020 | AS Supervisor, AS Librarian | Q2 2017 | Q4 2020 | In Progress | Staff track usage of materials
| Work with Planning Department staff on 1-2 new/updated resources and guides each year for individuals seeking historical home information and annually review usage of materials and resources by both City Staff and community members | AS Librarian | Q2 2017 | ongoing | Completed-In Progress | New historical home research worksheet created for public desks at City Hall and Library January 2017 (versions are regularly updated); Heritage Room Tour for Planning Dept. held March 2017; Research guide shared with Museum September 2017; Library secured a scanner from the State Library and it's currently used in the Heritage Room for historical research; staff attended a workshop on historical document preservation and digitization in June 2018; the Monrovia Legacy Project Online Collection launched in May 2018 with historical home information & research, as of September 2018 it had 4700 total searches

## SD Technology
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2018
Strategic Direction: Enhance Technology Enhance public access to state of the art technology tools and services
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Increase the reliability and speed of broadband and wifi services at the Library | Establish partnership with Califa for access to the statewide CENIC broadband network and work with the City's technology consultants, ACORN, and other staff to connect the Library to the broadband network by Q3 2018 | Library Manager | Q1 2017 | Q3 2018 | In Progress | CENIC Equipment Grant received February 2017; Equipment delivered October 2017; New Switch Installation December 2017; Califa, ACORN, and Spectrum worked together to launch the new service in late August 2018; the broadband speed has increased on average by 524% (78.36 download speed pre-launch vs. 488.9 download speed post-launch)
| Regularly review service to ensure continued speed and reliability, resulting in a 20% decrease in wifi concerns expressed by patrons within the first year of implementation | Library Manager | Q3 2018 | Q3 2019 | In Progress | Anecdotally, in FY 17/18 staff received an average of 1-3 complaints from patrons per month in regards to the wifi speeds within the library; since the implementation of CENIC broadband in late August 2018, staff have received no complaints
Goal 2: Evaluate and recommend a more efficient print management and reservation system | Review current print management and reservation system, meet with ACORN and vendors, and institute a new system with a cost savings of at least 5% by 2019 | Circulation Supervisor, Library Manager | Q2 2017 | Q4 2019 | Completed | Signed contract with Ventura Business Systems for updated, streamlined printing process with new copier/printer installed December 2017; new system saves the Library the cost of ink, paper, and lease agreements with Xerox
| Review new system regarding service level, budget, ongoing maintenance costs, and future technological changes one year after implementation to ensure costs are lower on average by at least 5% than the previous system | Supervisors | Q2 2018 | Q4 2020 | Completed | New copier/printer installed December 2017; reviewed costs in October 2018 and the new system resulted in a 15% decrease from the expenditure totals for the previous system ($2700 vs $2300); the new system is popular with patrons, particularly its credit card payment feature
Goal 3: Increase access to technology devices for use both inside and outside the Library | Assess need, review the budget, study best practices, and purchase and/or receive devices | Supervisors | Q1 2016 | Q2 2017 | Completed | Purchased 6 Kindles in 2016 and received donation of 3 telescopes in June 2017
| Create policies for use and circulation by Q3 2017 | Supervisors | Q2 2017 | Q3 2017 | Completed | Policies created for Kindles September 2017 and Telescopes June 2017
| Introduce telescopes and kindles for circulation by Q4 2017 | Supervisors | Q2 2017 | Q4 2017 | Completed | Telescopes launched in July 2017 and in their first year circulated 76 times since their introduction; Kindles soft launched in December 2017 and after some issues regarding security, Staff decided to provide the devices exclusively for use by the Literacy tutors and learners for programs like the book club
| Evaluate effectiveness of service and future needs with an increase in use of at least 10% by the second year of implementation | Supervisors | Q3 2017 | Q3 2019 | Waiting | Will review July 2019
Goal 4: Expand mobile-friendly access to Library resources | Ensure website, digital offerings, and content are responsive and/or mobile-friendly by 50% by 2020 and 100% by 2022 | Supervisors, AS Staff | Q3 2017 | Q4 2022 | Completed/ Ongoing | Responsive & mobile-friendly City website launched May 2017; Library Catalog launched June 2016; Summer Reading software, Beanstack, is responsive and launched an app June 2018; currently all digital resources offered by the Library are responsive and/or mobile-friendly
| Expand promotion of mobile-friendly services and resources by posting about them on social media 2-4 times each month | Library Manager | Q4 2017 | Q4 2018 ongoing | Completed/ Ongoing | Social Media Calendar established January 2018; Staff have posted 47 promos for online resources July 2017-April 2018; these online resources saw increases during the same time, with the usage of TumbleBooks going up 28%, Overdrive up 25%, and Zinio/RB Digital up 12%, compared to usage statistics from the same period last year; for FY17/18, staff posted a total of 58 promos for online resources; Overdrive finished the year up 32% from FY16/17

## SD Image
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2018
Strategic Direction: Enhance Image Strengthen the perception of the Library as a welcoming place for the community to gather
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Highlight for the community the multitude of opportunities offered by the Library | Establish a public relations team made up of 3-5 staff at various levels within the organization and create a list of the current means of promotion | Supervisors, AS & YS Staff, Circulation Staff | Q4 2017 | Q4 2018 | Completed | Members of the Public Relations Team include: Rebecca, Stefanie U., Victor, Julie, Josh, Erica, & Anush; meetings began September 2018; will complete promotions list at November meeting and start working on ideas for a comprehensive marketing plan
| Create a marketing plan, consisting of 3-5 marketing strategies and work with the City's public relations staff to ensure a citywide audience | Supervisors, Library Public Relations Team | Q4 2017 | Q4 2019 | Waiting
| Expand the Library's digital presence, more effectively using the new City website and social media platforms resulting in a 10% increase in audience reach by 2020 | Library Manager, AS Librarian | Q4 2018 | Q4 2020 | Completed/ Ongoing | Staff responsible for social media: Leila, Stefanie U., Anush, and Stephanie A.; the Library's official Facebook page grew with a huge jump in audience reach, with the daily average for FY17/18 at 733 versus 237 in FY16/17, a 209% increase; the offical Twitter account saw a 11.4% increase in Impressions versus last year and Staff worked on more consistently posting on the platform with an increase of 26.7% of total tweets in FY17/18 versus FY16/17; staff is using Buffer social media scheduling software as of 2018 to ensure consistent content on all three social media platforms (Facebook, Twitter, Instagram)
| Explore use of patron comment cards and targeted surveys and launch for use by 2018 at 25% of programs | YS Staff, Supervisors | Q2 2017 | Q2 2018 | Completed | YS Staff introduced survey cards for programs in Q2 2017; paper or verbal survey questions used at 30% of programs as of December 2017; Adult Services Staff started using program surveys in Spring 2018
Goal 2: Partner with the City Facility Staff to identify annual maintenance needs | Meet with facility staff and assess needs on a quarterly basis | Library Manager, Circulation Supervisor | Q2 2018 | ongoing | Completed/ Ongoing | Library staff meet regularly with Facility staff; created facility checklist January 2017
| Create maintenance needs plan and revisit on a quarterly basis | Supervisors | Q3 2018 | ongoing | Completed/ Ongoing | Created facility checklist January 2017
Goal 3: Better engage with the following key stakeholder groups - City staff, religious groups, and area service organizations | Continue building Library Express program for City staff, resulting in a library card holder rate among City staff of 90% by 2020 | Library Express Team | Q4 2017 | Q4 2020 | Completed/ Ongoing | Library Express Team, as of 2018: Miga & Julie; Introduced new library card design during National Library Card Signup Month September 2017 & encouraged signups by offering free replacement cards; City's new on-boarding process includes a stop at the library to sign up new employees for cards; for National Library Card Signup Month in September 2018, 73 staff received cards due to outreach efforts by staff; thanks to the work of the Library Express Team and the new on-boarding process, all full-time employees have library cards
| Promote Summer Reading Program to City staff, resulting in a program registration rate among City staff of 50% by 2019 | Library Express Team | Q3 2017 | Q4 2019 | In Progress | Library Express Team signed up 68 City staff during Summer Reading 2017 and expanded their promotion for Summer Reading 2018, with 157 staff members signed up over the summer (a program registration rate of 40%)
| Staff will regularly attend Healing Connections meetings and establish at least one program or partnership collaboration with a Healing Connections member by 2021 | Library Manager, YS Supervisor | Q3 2017 | Q3 2021 | Completed | Staff attended the 2017 Strategic Plan Meeting for the organization; Partnered with HC for March 4 Balance programs in March 2018, Talking With Your Teen and Express Yourself Through Art with a total attendance of 48 teens and parents at the two programs; continue to attend the monthly meetings when available
| Staff will explore partnership opportunities with Foothill Unity and the Interfaith Council by establishing a partnership agreement and/or collaborating on a program or service by 2021 | AS Supervisor | Q2 2018 | Q2 2021 | In Progress | Staff provided library services at the Foothill Unity Back to School Event in August 2018

## SD Staff
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2018
Strategic Direction: Enhance Staff Development Develop ways to invest in our team to be their best in the delivery of programs and services to our community
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Engage staff in the Strategic Planning process and Organizational Values | Clearly outline for all staff the organizational values as well as the Library Strategic Directions and SMART Goals with regular updates and discussions at monthly staff and departmental meetings by 2018 | Supervisors | Q2 2017 | Q1 2018 ongoing | Completed/ Ongoing | Part of agendas for monthly staff and departmental meetings
| Align professional development opportunities with organizational values and strategic directions, incorporating these elements into staff's annual evaluations by 2019 | Supervisors | Q2 2017 | Q1 2019 | Completed | Supervisors worked with Staff to develop individual evaluation goals that align and support the strategic plan to be included in their annual evaluations
Goal 2: Develop ways to celebrate the success and contributions of staff and volunteers | Work with Human Resources regarding new evaluation process to provide timely and meaningful feedback to staff within 60 days of their anniversary date by 2018 | Supervisors | Q3 2017 | Q1 2018 | Completed | The City introduced SuccessFactors online evaluation software June 2017; Updated evaluation process for Part-Time employees December 2017
| Work with the Volunteer Management Team (VMT) on volunteer feedback opportunities and methods, including creating a comment card and regular review of volunteer survey data that will result in positive volunteer testimonials and a higher retention rate than FY16/17 | AS Supervisor, Volunteer Team | Q4 2017 | ongoing | Completed | Comment card created for volunteers and was launched in January 2018; the staff Volunteer Team provided training for volunteers on handling difficult situations in June 2018 and provides ongoing training for new volunteers; these positive changes have resulted in higher retention rates for volunteers than in the past
| Work with the VMT to plan 2-4 Volunteer Celebrations each year | AS Supervisor, AS Librarian | Q3 2017 | ongoing | Completed/ Ongoing | In 2017, 4 events were held: Volunteer Celebration February 2017, TAB Recognition June 2017, Volunteer Celebration September 2017, and Literacy Holiday Potluck December 2017; as of October 2018, a Volunteer Celebration was held in March 2018 and Teen Volunteer Recognition in August 2018; the next Volunteer Celebration is planned for February 2019
Goal 3: Support regular and ongoing professional development for staff | Create professional development plan that includes meaningful outcomes and goals for library departments | BELC Team | Q2 2017 | Q4 2017 | Completed | 2017 BELC Team includes: Annette, Victor, Dan, Julie, Rebecca, Elizabeth, Carey; Created Professional Development Plan April 2017 that includes both library-wide and department goals
| Schedule 100% of staff for regular professional development time, at least three hours per month and maintain "Learning Hour" logs so newly acquired skills and knowledge can be included in yearly evaluations by 2019 | Supervisors | Q2 2017 | Q1 2019 | Completed | Learning Hours for all staff were introduced in early Spring 2017; Each staff member has 3-4 Learning Hours scheduled per month
| Establish annual in-house professional development workshop for staff | BELC Team | Q2 2017 | Q3 2017 | Completed | Staff Learning Summit held August 2017 with 23 in attendance and positive feedback from staff surveys after the event; the 2nd Annual Staff Learning Summit was held on August 9, 2018 with 23 attending and presentations on safety, Tinkercad, customer service, and library history; post-summit surveys from staff were very positive and plans are set for another summit in August 2019