## SD Experiences
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2021
Strategic Direction: Enhance Experiences Establish a welcoming space where the community enjoys enriched experiences
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Establish programming that aligns with organizational values and strategic directions with an emphasis on equity, diversity, and inclusion (Updated 2021 - SP Expansion) | Create a programming plan template that includes space to document at least 2 measurable outcomes | AS Programming Team, YS Staff, Supervisors | Q4 2017 | Q3 2018 | Completed | Staff have completed the programming plan templates for the Adult and Youth Services departments; the AS staff officially launched the plan in early 2019 and review the survey results and patron feedback on regular basis; the YS staff are regularly updating their plan to ensure it continues to align with 21st Century Skills across all age groups
| Annually review 30% of programs, measuring the outcomes listed in the program plan using patron surveys | AS Programming Team, YS Staff, Supervisors | Q4 2017 | ongoing | Completed-Ongoing | Staff launched the new programming plan January 2019; they currently review all programs to ensure they are meeting the outcomes listed in the program plan - 21st Century Skills and Active Mind, Active Life criteria; staff also continuously use feedback from patron surveys to ensure programming is meeting community needs
| 2021 SP EXPANSION ITEM: Create guidelines to incorporate virtual programming into the library's overall programming plan | AS Programming Team, YS Staff, Supervisors | Q3 2021 | Q4 2021 | In Progress
Goal 2: Review and refresh Library collections | Assess current print holdings, review usage statistics, and refresh 20% of the collection annually | Supervisors | Q1 2018 | ongoing | Completed-Ongoing | Weeded/refreshed Juv NF, Juv Fic, YA NF, Picture Books, M-Z Adult Fic, Large Print, DVDs, CDs, BkCD in 2017; equals 33.7% of total collection; received $7500 Bilingual Books Grant from State Library in FY16/17 & FY17/18 to refresh the juvenile Foreign Languages Collection; received $7500 CA Initiatives Grant from State Library in August 2018 to refresh the adult wellness and lifestyle collections as well as the juvenile parenting collection; in FY18/19, received $2000 from the Friends to update the Juv Nonfiction collection and $2000 to update and expand the MR Van's collection; in July 2019, received another $1500 from the Friends for the MR Van collection to support the 19/20 school year; staff updated the career and legal books in the Adult Services Area in early 2020; YS staff refreshed the parenting and J Fiction collections February-May 2020; staff inventoried the Young Adult collection in August 2020, with more collections to be inventoried over the coming year; Youth Services staff is finishing up an inventory of the section’s materials to ensure item location and information are correct to make locating and using the collection easier for staff and the public; all library staff assisted with the large scale update of the Adult Services collection, with all nonfiction titles now located on one side of the room to ease searching by patrons and all the fiction titles moved from the top and bottom shelves to provide easier access for those with mobility issues
| Review and update collection development policy, including guidelines on creating a collection with an inclusive lens (Updated 2021-SP Expansion) | Supervisors | Q4 2017 | Q1 2022 | Completed-Ongoing | Draft updated by supervisors August 2017; reviewed by staff September 2017; finalized & posted January 2018; staff are focusing on purchasing more BIPOC (Black, Indigenous, People of Color) authors as well as more "Own Voices" titles (authors and illustrators that create not with an observer's gaze, but with the cultural nuance from being an active member of that culture)
Goal 3: Review online resources | Assess current online resources and review usage statistics at the end of each fiscal year, cancelling services that show a decrease in use of 10% or more from the prior year | Library Manager, AS Librarian | Q3 2017 | ongoing | Completed-Ongoing | Canceled Gale Courses, Novelist, Newsbank, and Pronunciator due to low usage; Gale Courses ($5556) usage from FY15/16 to 16/17 50% decrease; Novelist ($2142) 39% decrease; Newsbank ($2235) 42% decrease; Pronunciator ($830) 80% decrease; in September 2017 introduced VetNow, a job skills resource for veterans that has had usage of 547 from July-December 2018; provide DuoLingo, a free language resource that offers online instruction in Spanish, Italian, French, and other languages; offer free access to the online site of the San Gabriel Valley News since June 2018; the State Library started providing free access for all public libraries in January 2019 to both English and Spanish editions of Encyclopedia Britannica's online version, Britannica Digital Learning, as well as the online New York Times site which has been visited 1,412 times since it's launch; the library applied for a state "Crisis Collection" grant in late April 2020 and received $5000 for ebooks to augment the collection in response to the Covid-19 crisis; the library recieved an additional Crisis Collection grant in October 2020 for $5000 to purchase even more ebooks for patrons; the State Library started providing free access to VetNow/JobNow in October 2020 to all libraries for 2 years, with the updated online resource being used a total of 1,246 times in FY20/21 (a 446% increase over the prior fiscal year); SCLC is offering all member libraries free access to PressReader for two years, starting October 2021; PressReader is an online platform that offers access to local, national, and international magazines and newspapers, including: L.A. Times, Rolling Stone, Vogue, and other popular titles as well as titles in multiple languages, audio features, and a mobile friendly app
| Ensure staff are familiar with online resources by providing trainings and updates every two months, resulting in 100% of staff having minimum knowledge of available online resources by 2021 | Clerks | Q1 2018 | Q2 2021 | Completed | Supervisors encourage staff to use Learning Hours to continuously update themselves on the online resources; staff have provided presentations at the three Staff Learning Summits on a variety of online resources to ensure all staff know what is available for our patrons
| Create and implement marketing plan for online resources with at least 3 strategies and evaluate the usage statistics annually | Library Manager | Q1 2018 | Q2 2018 | Completed | Starting January 2018: regular posts on social media, creating handouts, and introducing Tech Pop ups (ex. Tech Pop Up on Libby ebook app January 2018) or other impromptu mini-lessons; providing app overview & tech classes at local senior facilities during outreach; working with Marketing Team to create promotional materials for the Monrovia Reads Van to highlight online resources to local students
Goal 4: Evaluate physical space and make recommendations to create a healthy, safe, and more welcoming environment (Updated 2021-SP Expansion) | Assess library space and layout with current and future use in mind by surveying staff and patrons every two years, with a minimum of 25 respondents and up to 50, made up of various stakeholders (updated April 2019) | Supervisors | Q2 2018 | ongoing | Completed-Ongoing | Using survey data from the Strategic Planning process in late 2016 as a base, staff launched a space use survey focused on the Adult Services Area from November 2018-January 2019 and received 22 responses from patrons; during the Strategic Plan Review meetings with Staff in Feburary 2019, received 7 responses related to space use in the Adult Services Area; in November 2018, staff begin hourly head counts for a better sense of how and when the library is used by the community; acting in response to comments from parents for more interactive elements in the Youth Area, the library received funding from the Friends to purchase sensory boards that were installed November 2018
| Track current usage to determine need and then establish defined spaces for learning, technology, group study, and community use | Supervisors | Q2 2018 | Q2 2020 | Waiting | The hourly head count started November 2018 has been integrated into the monthly statistics taken throughout the year; the statistics provides basic usage data within the building that will be used when making decisions regarding defined spaces after the Library Park Redesign Project is completed; staff started reorganizing seating space in April 2021 to support physical distancing
| Identify at least 3 resources and/or individuals that can assist with space reorganization | Supervisors | Q1 2018 | Q3 2018 | Completed | Undisclosable, ABHE (Library Park redesign), and Linda Demmers/Libris DESIGN (a good resource of information)
Goal 5: Review options for expanding the indoor/outdoor space of the Library | Conduct community meeting to gather input and then work with the City to develop ideas for how best to utilize park space for the Library | Library Manager | Q2 2018 | Q2 2019 | In Progress | City staff met with ABHE for Library Park Redesign Fall 2017; met with Foundation June 2018; presented preliminary plans to Library Board July 2018 as well as the City Council and Friends in October 2018; staff presented updates at the December 2018 Foundation meeting and continue working on the project; due to the Covid-19 crisis, the project is temporarily on hold
| Assess community need and review best practices for a Café experience at the Library by visiting a minimum of four local library cafes by 2022 | Café Project Team | Q2 2020 | Q2 2022 | Waiting
| If a Café is feasible, work with the City to review legal and policy issues, and identify up to 3 potential locations as well as 3-5 potential partners | Café Project Team | Q2 2020 | Q2 2022 | Waiting
Goal 6: Support lifelong learning, with an emphasis on 21st Century skills for youth and "Active Mind, Active Life" programming for adults | Refresh current programming with a minimum of 20% of programming having an emphasis on 21st Century skills by 2021 | AS Programming Team, YS Staff | Q1 2018 | Q3 2021 | Completed | Staff started STEAM programming with Makerspace equipment funded by the Foundation in 2017; Youth Librarians received the Innovation Station Grant from the State Library in December 2017 and partnered with Oak Crest Institute of Science to purchase telescopes, circuitry kits, and other items that were used during Spring Break for their SciLab programs; after the success of SciLab in April 2018, the program was expanded for the summer reading program; for FY17/18, there was 88 STEAM programs for youth, which comprised 30.8% of total youth programming for that period; STEAM programming continued in FY18/19 with SciLab workshops onsite or at Oak Crest held quarterly; Adult Services Staff partnered with Copper Still Grill and Wingwalker Brewery to offer off-site programs like trivia nights and “Library Happy Hour” that have been very popular and reached a total audience of 262 across six events in FY18/19, with more planned for 2019/2020; starting in September 2019, Youth Services staff are offering twice monthly SciLab programs that include 3D printing, Lego Boost Robotics, and drop-in workshops on electronics, biology, and chemistry; due to the continued popularity of the 3D printer and TinkerCad workshops, staff printed 182 designs by patrons in 2019, an increase over the 162 designs submitted in 2018; staff continue to offer STEM virtual programming during the Covid-19 closure, with Makerspace videos on TinkerCad, the 3D printer, and the library's microscopes with a total of 451 views by the end of April; virtual storytime and craft videos in March and April were seen 7,198 times across the library's Facebook and Instagram sites; the library received a $2,500 grant from 3M to purchase materials for STEM virtual programming; staff produced 33 virtual storytime and craft videos in May & June with a total of 5,394 views; STEM virtual programming continues to be popular, with videos on TinkerCad, Thingiverse, 3D printing, and library microscopes having a total of 1,782 views in May & June; received a 2021 Book To Action grant in October 2020 from the state library to purchase books and provide programming around the theme of sustainability and environmental justice, particularly important in light of the recent Bobcat Fire and wildfires across California, with programming taking place in 2021 that will highlight the science and social issues related to wildfires; staff produced a total of 32 virtual storytime and craft videos in August and September, with 4,775 views; staff offer STEM virtual programming, including videos on inertia, exothermic reactions, 3D design, diffusion, and different types of rocks, with a total of 1,436 views in August and September; staff produced a total of 32 virtual storytime, craft, makerspace, and informational videos in November and December 2020, with 1,838 views across the library’s social media accounts and on the city’s YouTube channel; since the start of the closures, virtual programs have been viewed a total of 30,502 times (March 13-January 2); staff secured a grant totaling $11,984 in March 2021 to purchase equipment and supplies for virtual programming for families and teens that emphasize STEM and 21st Century skills building; staff produced a total of 61 virtual storytime, craft, makerspace, and informational videos January through March 2021, with 4,467 views across the library’s social media accounts and on the city’s YouTube channel; Youth Services provided in-person Storytime in the Park on select Saturdays in June and July 2021, with a total of 57 at the first two programs; staff continues to provide in-person Storytime in the Park on Wednesdays and Saturdays as well as teen events and other programs, with 492 attendees in August & September 2021
| Partner with the school district and other educational organizations within the community to expand the offerings and promotion of youth programming with staff attending 2-4 school or PTA meetings per year | YS Staff | Q2 2018 | ongoing | Completed-Ongoing | Staff has partnered with Monrovia Reads and MUSD on the Monrovia Reads Van project; attended the annual Santa Fe Parent Literacy Night October 2017; staff attends monthly Healing Connections meetings at the high school; hosts monthly meetings for local school librarians in the Library's Heritage Room; staff attended Open House events at the schools March-May 2019; the library provided services and access to participation in the Summer Reading Program for MUSD summer school students June-July 2019 at Mayflower & Bradoaks; in response to positive feedback from school staff and students, the Great Stories Club is returning to Canyon Oaks High School for another year, with library staff expanding the program beyond the grant-funded four months to the entire 19/20 school year; staff attended Back to School Nights at the local elementary, middle, and high schools in August and September, reaching a total of 621 students and their families
| Review current programming for adults and seniors and identify areas where new or refreshed ideas are needed, implement 3-5 programs and/or services with measurable outcomes by 2019 | AS Supervisor, AS Librarian | Q1 2018 | Q3 2019 | Completed-Ongoing | Staff provide monthly visits to local senior facilities and a survey of their residents has resulted in new ideas for programs like Silver Screen Cinema, that was introduced September 2018; staff provide books and technology help on an continuous basis as well as modified library programs to local facilities, including a current events program on voting, a training for seniors on using Lyft, and workshops on ebooks; since August 2018, staff has partnered with the activities coordinator at Heritage Park and Regency Court to visit monthly with original programming that enhances their sociability, hand/eye coordination, dexterity, and mental well-being; activities include: painting, yarn craft, and hula dancing; staff received a $3000 Value of Libraries grant from the State Library in March 2019 that is being used to enhance activities during senior outreach; the library has received free dementia and Alzheimer's activity kits, funded by a state grant, that will support staff as they provide outreach to local senior facilities and memory care groups as well as kits that will be available for checkout by patrons
| Identify and meet with potential community organizations that cater to seniors in the community resulting in 3-5 visits by library staff by 2019 | AS Supervisor, AS Librarian | Q2 2018 | Q1 2019 | Completed | Staff has partnered with the Community Center's Senior Group for Senior Lunch & Learn visits; provided presentations on library services and a roving collection to both the Senior Group and local facilities; regularly partners with Brookdale, Regency Court, and Heritage Park; presented on volunteer opportunities for Older Adults at Providers Group meetings; staff visits local senior facilities on a regular basis with a total of 24 visits that reached 192 seniors from July 2018-June 2019
| Implement new or expanded "Active Mind, Active Life" adult and senior programming and regularly review it's impact based on feedback from the community and measurement of outcomes using surveys with a minimum of 10% of program attendees responding | AS Supervisor, AS Librarian | Q4 2018 | Q3 2019 | Completed-Ongoing | Staff began providing scaled down versions of library programs at local facilities for seniors, including a DIY Garden Workshop in April 2017 and Hawaiian dance demo in August 2018; provided surveys in Summer 2018 for Older Adults and launched new programming in September 2018 in response to requests, including a movie series and more mindfulness programming; programs continue for seniors in FY19/20 and will be enhanced using the Value of Libraries grant; staff held several live virtual holiday programs in December 2020 to ensure the community was still able to enjoy annual traditions like the Holiday Sounds concert and Santa Storytime even during a pandemic; Veterans staff, who provided support to 58 veterans and their families in August & September, presented information about the Veterans Resource Center at the National Veterans Forum in September, inspiring other organizations across the country to duplicate our program's successes

## SD Access
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2021
Strategic Direction: Enhance Access Expand opportunities for the community to access the Library and its resources
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Evaluate and recommend Library hours of operation to meet the needs of the community | Review information received from community and assess staffing levels and resource allocation needed by Q4 2019 | Circulation Supervisor, Library Manager | Q4 2017 | Q4 2018 Q4 2019 | Waiting | Reviewed survey results and feedback received from the public; reviewing data from the ongoing hourly head count statistical project launched in November 2018, which provides more complete data on how and when the library is used by incorporating hourly head counts into the public desk statistics forms; supervisors have met several times to assess staffing levels needed for any changes to the hours of library operation and a decision was made to wait until after the Library Park Redesign Project is completed since the expansion of the library's space will impact how each area is staffed which in turn would impact any staffing assessments made regarding operating hours
| If a change in hours is made, market and promote new operating schedule to the community resulting in an increase of library visits by 10% within the first year of the new schedule being implemented | Circulation Supervisor, Library Manager | Q2 2019 | Q3 2021 | Waiting
Goal 2: Evaluate and recommend Library needs for underserved populations, with a focus on Southern Monrovia, as well as at-risk populations (Updated 2021 - SP Expansion) | Conduct a random survey of the community with a minimum of 50 respondents from underserved or at-risk populations and review information received to assess needed services (Updated 2021-SP Expansion) | YS Staff, Supervisors | Q1 2018 | Q2 2020 | Completed-In Progress | Had 22 survey respondents when the Monrovia Reads Van visited Plymouth Elementary May 2018; surveyed 10 residents at Heritage Park in fall 2018 regarding potential library services and programs that would best fit their needs, based on responses will create opportunities for residents to connect with local resources using the City's GoMonrovia/Lyft partnership; received 7 surveys from seniors at Heritage Park in winter 2019; surveyed 17 parents and students at Plymouth in May 2019 regarding mobile library services; will continue to incorporate surveys into programs at Station Square and other S. Monrovia locations, such as visits to Huntington Oaks Shopping Center
| Assess staffing levels and existing budget and explore redeploying existing resources if new or expanded services are needed with a minimum of two new and/or expanded services launched by 2021 | Supervisors | Q1 2018 | Q4 2021 | Completed-In Progress | Monrovia Reads Van launched March 2018, servicing Plymouth Elementary; Summer Reading Kickoff June 2018 was held at Station Square with 202 in attendance; during Summer 2018, the Monrovia Reads Van visited the Huntington Oaks Shopping Center on a monthly basis; staff make monthly visits to Heritage Park in S. Monrovia, providing activities & library services to its residents; the Monrovia Reads Van partnered with Huntington Oaks for a holiday visit in December 2018 and returned in the summer in June 2019 to partner with other retailers for a Fun in the Sun event that attracted over 200 people; received $55,000 grant from State Library to expand and enhance family literacy services, with a focus on creating more informed parents and guardians regarding early literacy; select staff received training from Abriendo Puertas/Opening Doors, a nationally recognized early literacy program, in June 2019; the new Family Literacy program launched in September 2019 with parents from the Adult School; the Monrovia Reads Van provided library services to students from Plymouth, who visited the van 1,026 times and checked out 527 books during the 18/19 school year; the van has expanded service during the 19/20 school year to include regular visits to Santa Fe Middle School as well as Plymouth; in November 2019, staff met with the principal from Plymouth Elementary to discuss additional ways to bring library services to their students & S. Monrovia families; the Monrovia Reads Van visited Huntington Oaks Center in December 2019, providing library services, storytime, and activities to 140 children and their families; library partnered with StoryCenter, a nonprofit that supports storytelling as a method to build community, to host an online Story Circle workshop in April 2020 as a way for adults and teens to share their story during stressful times, and in response to survey results from adults interested in programs that focus on wellbeing; the library received a $42,580 Library and Technology Services grant from the state in June for FY21/22 that will allow the library to install a remote locker for holds retrieval and book returns in Recreation Park, expanding access to library services across the community
| If new or expanded services are created, establish a marketing plan and promote new services to the targeted populations, resulting in a minimum increase in use/visits by 10% after two years | Supervisors | Q1 2018 | Q2 2022 | In Progress | Marketing Team started meeting in September 2018 and meets on a regular basis; staff from both the Marketing Team and the Monrovia Reads Van have discussed ideas on how to promote new services related to the van in Southern Monrovia; with the launch of the new library events calendar in July 2019, the van's visits were incorporated into the calendar to promote where it will be in the community on any given day, including its visits to Plymouth & Santa Fe
Goal 3: Evaluate and recommend ways to enhance the mobility of and equitable access to Library services (Updated 2021-SP Expansion) | Review best practices for providing mobile services and identify three potential locations for hosting outreach with community partners, holding at least 4 meetings with partners by 2020 | Supervisors | Q1 2018 | Q2 2020 | Completed | Using the Monrovia Reads Van, a collaboration with community partners: Monrovia Reads, the Library Foundation, Foothill Credit Union, and other corporate sponsors, staff have engaged in outreach at the local elementary schools, participating in community events such as MAP and the Spring Egg Hunt each year; the Monrovia Reads Van was at the Mayflower Family Fun Night in April 2018 and the Wild Rose PTA Picnic in February 2019; the van is also a regular participant at the annual Foothill Unity Back to School event in August and the MUSD summer school program; staff attends monthly Monrovia Reads meetings and meets with MUSD staff on a regular basis as well as hosting monthly meetings with school librarians at the Library; in the first year of the program (3/6/18-3/6/19), the van served 6,594 people, created 151 library cards, and circulated 2,666 books at a total of 195 outreach visits; in FY18/19, the MR Van participated in 161 school & community visits, including MAP events throughout the year, afterschool & summer school visits, events at Huntington Oaks Center, Wingwalker Brewing, and the Summer Reading Kickoff in June 2019; the Monrovia Reads Van expanded service during the 19/20 school year to include regular visits to the local middle schools, high schools, and the Canyon Early Learning Center; the van’s service year was abbreviated due to the Covid-19 crisis and the resulting closure of local schools but the MR Van was still successfully expanded during the 19/20 school year, serving 4,508 students with 43 library cards created, 1,631 books borrowed, and 102 visits from July 2019-March 2020; in response to the library's closure due to Covid-19, staff launched Curbside Pickup Service on July 6, a completely contactless holds service, and in the first week had 522 items borrowed and assisted a total of 256 patrons via email, phone, or text with overwhelmingly positive feedback from enthusiastic patrons; due to travel restrictions put into place in response to the pandemic, several Literacy learners were unable to travel back to the United States but they have been able to continue their one-on-one meetings and participation in the weekly book clubs and conversation classes virtually via Zoom thanks to guidance from Victor and Jade, who provided mini-tutorials on the platform for each learner and tutor in the program ensuring continued access across not only the city but the entire world; the library has generated a total of 117 ecards since the closures began, providing access to online resources and curbside holds pickup; in the first three months of Curbside Service (July 6-October 10) we had 13,090 items borrowed and assisted a total of 3,786 patrons via email, phone, or text with overwhelmingly positive feedback from enthusiastic patrons; the library has generated a total of 194 ecards in the first 7 months of the Covid closures (March 13-October 10), providing access to online resources and curbside holds pickup; kits were made for patrons to reserve online and pick up via curbside, so they could participate in the Adult Services’ Gather & Make live Zoom programs in October, providing access to original library programming that allowed patrons the chance to interact with staff and one another; in the first six months (July 6-January 9) had 21,349 items borrowed and assisted a total of 6,255 patrons via email, phone, or text; the library has generated 289 ecards in the first 10 months of the closures (March 13-January 9); activity kits were launched in January for families to reserve online and pick up via curbside, so they could participate along with staff in virtual craft and STEM programs, providing access to original library programming in the new year; the library has generated a total of 384 ecards in the first year of the Covid closures (March 13, 2020-March 13, 2021), providing access to online resources and curbside holds pickup; in the first 9 months (July 6-April 3) of Curbside, 30,679 items have been borrowed and staff assisted a total of 9,255 patrons via email, phone, or text; Book to Action activities were designed to reach people in a variety of ways to ensure easy access, including: DIY kits for seed bombs and composting available via Curbside Pickup, virtual film screenings, interaction with local experts on Instagram and Facebook Live, as well as an author talk via Zoom; Book to Action activities in May included more virtual film screenings; interaction with local experts on Instagram Live; as well as a conversation with a local Chumash Fire Keeper and Indigenous Activist on fire and land stewardship via Zoom; the Book to Action programs in April & May had a total of 1,452 participants across 15 programs; the library launched Curbside Pickup Service last year, a completely contactless holds service, and from July 6, 2020 - April 30, 2021 a total of 33,844 items were borrowed and staff assisted 10,159 patrons via email, phone, or text; while the library reopened to the public on May 3rd, Curbside continues in a modified form as an option for patrons when using the library; from March 13, 2020-April 30, 2021, the library created 446 ecards to provide access to online resources and curbside holds pickup during the library’s closure; in honor of National Family Literacy Week in September 2021, Literacy staff created family literacy kits with books, activities, and other elements for families to pick up at the library with a total of 20 kits being reserved & picked up; the new grant-funded Monrovia Reads Van was delivered in September and staff is working with the DMV and Public Works to get the electric, customized vehicle ready for service; library staff resumed service to the local schools with the Monrovia Reads Van, coordinating arrival times and setup with each school site’s administration to ensure a safe, streamlined experience for students and their familie; in the first month back, staff provided services to a total of 267 students who borrowed 123 books and created 21 new library cards; the MR Van has provided services to a total of 14,094 students and community members since the program launched in March 2018 (as of September 2021)
| If new mobile services are created, establish a minimum of 3 outcomes and at least 5 goals to measure effectiveness, including an annual report for the Library Board's review | Supervisors | Q2 2018 | Q4 2020 | Completed | Staff drafted a plan with 3 outcomes and 5 goals and reviewed it with the Monrovia Reads Van Team; have incorporated the plan into the activities and directions for the 18/19 school year; outcomes were included in the annual Monrovia Reads Van report to the Library Board in June 2019; the next annual report will take place at the June 2020 Library Board meeting
| If new or expanded mobile services are created, design a marketing plan and promote new services to community resulting in a 10% increase in use and/or program attendance after second year | Supervisors | Q2 2018 | Q2 2022 Q4 2022 | In Progress | Marketing Team have met with the Monrovia Reads Van Team to discuss a marketing plan; promotional materials were created for the launch and have been expanded for the 18/19 school year; in July 2019, the new library events calendar launched, with the van's visits incorporated into the calendar's listing of events; the second year of service for the van will be the 19/20 school year which means staff will review attendance numbers for the 20/21 school year to evaluate impact of marketing and promotion of the program; due to the pandemic, schools closed in March 2020 and reopened in August 2021 delaying accurate usage statistics for van service; the MR Van returned to the schools in September 2021 and will review statistics after the completion of the 21/22 school year
| 2021 SP EXPANSION ITEM: Provide information in multiple languages and formats to meet accessibility needs | Supervisors | Q3 2021 | Q2 2022 | Completed-In Progress | Staff are posting library programs on YouTube, which allows closed captioning options for viewers; the library catalog offers the option of using it in an English or Spanish language mode; TumbleBooks, an online ebook platform for kids, offers titles in English, Spanish, and French; JobNow & VetNow offer language options on their site for English, Spanish, and French to ensure veterans and job seekers are able to access the support they need; PressReader, a new online resource provided by the local library consortium in September 2021, offers newspapers and magazines in multiple languages as well as offering audio options for patrons with limited vision

## SD Partnerships
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2021
Strategic Direction: Enhance Partnerships Establish strategic partnerships and increase community engagement
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Develop or expand partnerships with social services providers, community organizations, and local businesses (Updated 2021-SP Expansion) | Identify 3-5 potential community and City partners and establish strategic networks of support | AS Staff | Q2 2020 | Q3 2021 | Completed-In Progress | Staff has identified Foothill Workforce Development Board (FWDB), Foothill Unity Center, Dementia-Friendly Monrovia (DFM), and LA County Dept. of Mental Health (LAC-DMH) as community partners and networks of support; the library partnered with LAC-DMH on a wellness fair in 2017 & staff training in August 2018; staff partnered with FWDB on job skills training for Veterans and a workshop for English language learners attended by Literacy staff October 2018; staff attends DFM meetings on a regular basis; staff participates annually in the Foothill Unity Back to School event and took a tour of the Center's facility in February 2019; the library promotes DFM materials and received free dementia and Alzheimer's activity kits, funded by a state grant, that will support staff as they provide outreach to local senior facilities and memory care groups as well as making kits available for checkout by patrons in early 2020; staff partnered with the local American Legion Women’s Auxiliary to support hospitalized military personnel with a donation box in the Library Lobby during the months of December 2019 and January 2020, gathering personal items and craft supplies to support veteran wellness and recovery; staff partnered with the Foothill Workforce Development Board for a Veterans Career Expo hosted at the library in early March 2020 with 40 attendees; staff partnered with the Monrovia Rotary Club and the Monrovia Public Library Foundation to reupholster the book-themed furniture in the Youth Services Area in April 2020 to ensure these well-loved pieces will be shiny and new for returning patrons; the library partnered with the Foothill Unity Center on the Fall Reading Program in October 2020, with a new book being donated to the center for each person that completes the program; the library once again partnered with the Foothill Unity Center on the Holidays Around the World Reading Program in December, with a total of 100 new books being donated to the center for families in need; staff, seeking to support both mental and physical wellbeing, collaborated with the Recreation Team on the Family Adventure From Home: Spring Fitness Challenge series, providing virtual storytimes for the weekly sessions, as well as participating in the annual Spring Egg-stravaganza in April 2021 with a storywalk and other activities for over 700 participants at the event; staff is collaborating with the Recreation Team on Recess in the Park events in July and August 2021, providing a storywalk and other activities for the families; staff collaborated with the Boys & Girls Club, as the recipient of this summer’s Read to Give Summer Reading Program, with a new book donated to the organization for every person that participates in the program. As of June 30, 96 have signed up for summer reading, logging 53,545 minutes of reading; staff worked with the Friends of the Monrovia Public Library on ways to safely reopen the Friends book store on September 4th after it had been closed for 18 months due to the pandemic; in partnership with the Recreation Division, the library participated in the Wine Walk in October 2021 with help from Library Board members, highlighting all the resources the library has to offer to the event’s 600 participants; the library partnered with a local community member to host a Lego Derby for younger kids at the Soap Box Derby event in Old Town in September
| Review information received from the community and assess best practices for providing social services that promote mental wellbeing, health, and growth (Updated 2021-SP Expansion) | AS Staff | Q4 2020 | Q2 2021 | Completed-In Progress | Staff visited Patriotic Hall in October 2016 to discuss social services that are available for veterans with federal and stafe officials; currently working with CalVet to coordinate regular visits by the local benefits officer at the VRC to begin in summer 2019; are scheduling visits for Azusa, Glendale, and Pasadena public libraries to learn more about their partnerships with local social service agencies; staff toured the Foothill Unity Center in Februrary 2019 and discussed ways to expand the partnership to bring library services to their clients; after reviewing training provided at other libraries, Ryan Dowd's Homelessness in Libraries online training series was purchased to provide all library staff and select city staff access to the year-long training program in FY18/19 and after positive feedback from staff, the program was extended for FY19/20; partnered with Foothill Unity Center on their Back to School Donation Drive by collecting items from the community June & July 2019 and participated in the center's Back to School Event at Santa Anita in August 2019 reaching 150 children & their families; have collaborated with Dementia-Friendly Monrovia (DFM) by participating in monthly meetings, providing information for local Alzheimer social services at public service desks, and offering memory-care tours and activties for local senior groups; provided informational materials to the public from Dementia-Friendly America starting in August 2019; longtime community partners, the Rotary Club of Monrovia, donated 24 brand new books to the library’s collection in January 2021 in honor of their club’s speakers
| Evaluate 100% of the currently offered social services within the Library for any duplication of effort and ensure the maximum effectiveness of Library staff and resources | AS Staff | Q4 2020 | Q2 2021 | Completed-In Progress | Staff has reviewed social services at the library that are provided by partnerships with CalVet, Foothill Unity Center, and Dementia Friendly Monrovia to ensure maximum effectiveness of these relationships and the ongoing services they provide the community
| If new or additional services are needed, promote to community and targeted populations most in need, and then measure ongoing effectiveness with a survey that has at least 20 respondents one year after new service is launched | AS Programming Team, YS Staff, Supervisors | Q4 2021 | Q4 2022 | In Progress | A new service of offering access to a VSO benefits officer on-site at the Veterans Resource Center on a regular basis started in August 2019 and the response has been incredibly positive with advanced appointments filling his weekly visit; staff is working with local senior facilities regarding memory-care support that has included library tours for residents and activities; staff has added dementia-friendly materials for seniors and caregivers as part of the ongoing partnership with Dementia Friendly Monrovia; from August-December 2019, 121 veterans and their families were provided support and services during the weekly VSO on-site visits at the Veterans Resource Center; due to the pandemic, on-site VSO service was temporarily suspended from March 2020-August 2021; the County Veterans Service Officer (VSO) resumed on-site support in August with office hours on Mondays & Thursdays while a representative from the Veteran Peer Access Network (VPAN) started on-site service on Tuesdays, supporting veterans as they work with the VA and other governmental agencies; the VSO helped 64 veterans while the VPAN representative assisted an additional 29 in August & September
Goal 2: Develop and expand partnership with MUSD regarding Literacy, Veterans, and Youth Services | Meet with MUSD staff, including school librarians, teachers, and principals, to assess current partnership and discuss ongoing and future needs as related to Literacy, Veterans, and Youth Services | Supervisors, Literacy Coordinator, AS Librarian | Q4 2018 | Q2 2022 | Completed-In Progress | Staff met with MUSD 3 times from August 2017 through February 2018 regarding the Monrovia Reads Mobile Literacy Program; the Library hosts the school librarians' monthly meeting in the Heritage Room; the Literacy Coordinator offers regular tours to students at the Adult School as well as hosting classes and leading workshops on the Adult School campus; after receiving the Great Stories grant from the American Library Association, staff partnered with Canyon Oaks High School in January 2019 to bring a monthly book club to the school for 11th & 12th graders deemed by their teachers to be at risk, participating in the club allows them to earn credits for school and they receive the monthly titles to keep for their own personal library; all the titles of the Great Stories Book Club share the theme of heroism and being the hero of your own story; a total of 12 students participated in the Great Stories Book Club January-May 2019 and based on positive feedback, staff applied for the Great Stories grant again-recieving funding for four months-and decided to provide the book club for the entire 19/20 school year; the first meeting took place August 2019 and staff meets monthly with the students and their teacher; staff attended Back to School Nights at the local elementary, middle, and high schools in August and September, reaching a total of 621 students and their families; staff met with the principal from Plymouth Elementary in November 2019 to discuss additional ways to bring library services to Plymouth students & S. Monrovia families; during the library closure in March and April, Literacy virtual conversation classes and meetups continued with 120 participants, ensuring support for Adult School students who are active participants in the library's weekly conversation classes; staff partnered with the Monrovia Duarte Black Alumni Association (MDBAA) on a Black History Month Celebration event in February 2020 that included music, crafts, and a readers theater presentation by teens with a total attendance of 190; Literacy virtual conversation classes and meetups continued with 244 participants in May and June 2020; the Veterans program has gone online with virtual meetings and Mabel has been working with the state’s Veterans Connect team on virtual trainings for the VRC volunteers to keep them updated on current resources and services for veterans and their families; Mabel served as a panelist on a Veterans Connect virtual training in May 2020 and Victor was a guest speaker for a SCLLN (Southern California Library Literacy Network) statewide webinar also held in May; Victor has continued to act as a guest speaker at various SCLLN meetings over the past few months; Youth Services staff started meeting with MDBAA in July 2020 and continue to meet on a regular basis to plan the virtual Black History Month Celebration in February 2021; Literacy virtual conversation classes, book clubs, and meetings continue with 252 participants in August and September and 45 online meetings; Literacy conversation classes, book clubs, and meetings continue virtually with 40 programs and 226 participants in November and December; staff hosted a series of virtual outreach visits for T-K and Kindergarten classes from Plymouth in November 2020, with the 5 classes enjoying trivia, games, and socializing with a total attendance of 27 students; staff collaborated with the Monrovia Duarte Black Alumni Association (MDBAA), to host special storytimes for a virtual Black History Month Celebration in February 2021, with 4 storytimes that were viewed 120 times; Adult Literacy services continue virtually with 73 programs and 429 participants in the first three months of 2021; staff hosted virtual outreach visits with 5 more classes from Plymouth in January and February 2021, with 151 students learning how to search the catalog; enjoying booktalks, storytime & songs; as well as movement activities; Monrovia Reads Van staff participated in outreach visits in June at the four MUSD summer school sites hosted by Boys & Girls Club this year, with books, library cards, and fun activities for the students with six more visits planned for July & August; in June 2020, staff served a total of 62 students at two summer school sites, checked out 24 books, and created 2 library cards; since Covid closures began in March 2020, Literacy staff have provided a total of 330 virtual programs for 2,072 participants, ensuring continued support for all participants in the library's Literacy program (March 2020-June 2021); from July-September 2021, Literacy staff provided 16 virtual programs for 135 participants, with a brief break for summer vacations in August
| Draft action plan with 3-5 outcomes and 5-7 goals to measure the impact of expanded partnerships and related activities | Supervisors, Literacy Coordinator, AS Librarian | Q2 2019 | Q4 2022 | In Progress | Will incorporate elements of the Mobile Literacy Van outcomes and goals into the action plan
Goal 3: Develop and expand partnership with local historical organizations and related City departments | Meet with local historical organizations 3-5 times per year over the next three years to assess current partnerships and discuss ongoing and future needs in preserving the City's rich heritage and local history resources | Library Manager, AS Supervisor | Q2 2017 | Q4 2020 | Completed-In Progress | Staff held meetings with Legacy Project and Museum; purchased PastPerfect software December 2017 for historical collections; launched the website for the Legacy Project's historical online collection in May 2018 & holding places for future online collections from the Museum and Library; met with Community Development staff in November 2018 to coordinate the relocation of historical plans on microfiche to the Library; staff continues to work closely with the Legacy Project Team to maintain and update the online collection
| Promote historical research opportunities and resources available at the Library resulting in a 15% increase in the use of historical materials by 2020 | AS Supervisor, AS Librarian | Q2 2017 | Q4 2020 | Completed | Staff regularly track usage of materials; with the launch of the Monrovia Legacy Project's online collection in May 2018, use of historical items have greatly increased; the online collection has seen an increase of 56% as of March 2019, with 4,744 searches in FY18/19 and 7,784 total searches since it's launch in May 2018; for FY18/19, the online collection had a total of 6,046 searches while 202 Heritage Room materials were accessed (vs. 186 in FY17/18); at the annual Literacy Fundraiser in September 2019, attendees participated in a library-wide scavenger hunt that highlighted various library services, including the Heritage Room and it's historical materials; the Legacy online collection had a total of 3,616 searches in FY19/20, a decrease from the previous year, with staff working on enhancing promotion of the collection via social media
| Work with Community Development/Planning Department staff on 1-2 new/updated resources and guides each year for individuals seeking historical home information and annually review usage of materials and resources by both City Staff and community members | AS Librarian | Q2 2017 | ongoing | Completed-In Progress | New historical home research worksheet created for public desks at City Hall and Library in January 2017 (versions are regularly updated); Heritage Room Tour for Planning Dept. held March 2017; Research guide shared with Museum September 2017; Library secured a scanner from the State Library and it's currently used in the Heritage Room for historical research; staff attended a workshop on historical document preservation and digitization in June 2018; the Monrovia Legacy Project Online Collection launched in May 2018 with historical home information & research available 24/7 to users around the world; staff attended a historical documents digitization workshop in October 2019, related to the state grant that provided the scanner

## SD Technology
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2021
Strategic Direction: Enhance Technology Enhance public access to state of the art technology tools and services
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Increase the reliability and speed of broadband and wifi services at the Library and within Library Park (Updated 2021-SP Expansion) | Establish partnership with Califa for access to the statewide CENIC broadband network and work with the City's technology consultants, ACORN, and other staff to connect the Library to the broadband network by Q3 2018 and expand wifi connection within Library Park by Q4 2021 (Updated 2021-SP Expansion) | Library Manager | Q1 2017 | Q4 2021 | Completed/ Ongoing | CENIC Equipment Grant received February 2017; Equipment delivered October 2017; New Switch Installation December 2017; Califa, ACORN, and Spectrum worked together to launch the new service in late August 2018; the broadband speed has increased on average by 578% (78.36 download speed pre-launch vs. 531.57 download speed post-launch March 2019); staff is currently working with ACORN to put into place routers on the library roof to expand wifi service to the park area
| Regularly review service to ensure continued speed and reliability, resulting in a 20% decrease in wifi concerns expressed by patrons within the first year of implementation | Library Manager | Q3 2018 | Q3 2019 | Completed | Anecdotally, in FY 17/18 staff received an average of 1-3 complaints from patrons per month in regards to the wifi speeds within the library; since the implementation of CENIC broadband in late August 2018, staff have received no complaints
Goal 2: Evaluate and recommend a more efficient print management and reservation system | Review current print management and reservation system, meet with ACORN and vendors, and institute a new system with a cost savings of at least 5% by 2019 | Circulation Supervisor, Library Manager | Q2 2017 | Q4 2019 | Completed | Signed contract with Ventura Business Systems for updated, streamlined printing process with new copier/printer installed December 2017; new system saves the Library the cost of ink, paper, and lease agreements with Xerox
| Review new system regarding service level, budget, ongoing maintenance costs, and future technological changes one year after implementation to ensure costs are lower on average by at least 5% than the previous system | Supervisors | Q2 2018 | Q4 2020 | Completed | New copier/printer installed December 2017; reviewed costs in October 2018 and the new system resulted in a 15% decrease from the expenditure totals for the previous system ($2700 vs $2300); the new system is popular with patrons, particularly its credit card payment feature
Goal 3: Increase access to technology devices for use both inside and outside the Library to help address the issue of digital divide (Updated 2021-SP Expansion) | Assess need, review the budget, study best practices, and purchase and/or receive devices that will provide increased access for those who lack ready access to technology items, with a focus on digital items needed for career advancement (Updated 2021-SP Expansion) | Supervisors | Q1 2016 | Q2 2017 | Completed/ Ongoing | Purchased 6 Kindles in 2016 and received donation of 3 telescopes in June 2017; received donation of ISS-Above device that provides live streaming of the International Space Station and set it up in the Lobby in April 2018; in October 2020, the state library provided a two year subscription to Brainfuse’s updated JobNow/VetNow, an online resource site for job skills and veterans, and since its launch it has been visited a total of 475 times
| Create policies for use and circulation by Q3 2017 | Supervisors | Q2 2017 | Q3 2017 | Completed | Policies created for Kindles September 2017 and Telescopes June 2017
| Introduce telescopes and kindles for circulation by Q4 2017 | Supervisors | Q2 2017 | Q4 2017 | Completed | Telescopes launched in July 2017 and in their first year circulated 76 times; Kindles soft launched in December 2017 and after some issues regarding security, staff decided to provide the devices exclusively for use by the Literacy tutors and learners for programs like the book club; the Kindles have been very popular with the Literacy book club members, since it provides large print options and easier access to ebook versions of the title the club is discussing; the Library Foundation approved the purchase of two new 3D printers in December 2019, which will allow enhanced access to learning STEM skills at monthly library workshops as well as the ability for staff to take the library’s smaller 3D printer off-site for outreach visits
| Evaluate effectiveness of service and future needs with an increase in use of at least 10% by the second year of implementation | Supervisors | Q3 2017 | Q3 2019 | Completed | Regular repairs occur three times a year and prevent the telescopes from circulating 6-8 weeks over the course of a year; overall, the circulation data from FY17/18 to FY18/19 has remained steady but the demand is still high as evidenced by the telescopes consistently being one of the library items with the most reserves; currently there are 21 reserve requests for the telescopes, as of January 2020; since their launch, the three telescopes have circulated 168 times which gives them a turnover rate of 56, the highest collection turnover rate within the library; the Library Foundation generously is supporting the purchase of new teleconferencing equipment for virtual classrooms and workshops as well as filming equipment and software to be used by staff as a way to enhance and expand the library's virtual programming for all ages
Goal 4: Expand mobile-friendly and self-service access to Library resources (Updated 2021-SP Expansion) | Ensure website, digital offerings, and content are responsive and/or mobile-friendly by 50% by 2020 and 100% by 2022 | Supervisors, AS Staff | Q3 2017 | Q4 2022 | Completed/ Ongoing | Responsive & mobile-friendly City website launched May 2017; Library Catalog launched June 2016; Summer Reading software, Beanstack, is responsive and launched an app June 2018; currently all digital resources offered by the Library are responsive and/or mobile-friendly; a new library events calendar software was launched July 2019 for a more streamlined and intuitive experience with a mobile-friendly and responsive design that works across various devices; aided by the user-friendly interface of the Overdrive app, Libby, ebook interest and usage continues to grow with 12,620 checkouts since the start of the 19/20 fiscal year
| Expand promotion of mobile-friendly and self-service resources by posting about them on social media 2-4 times each month | Library Manager | Q4 2017 | Q4 2018 ongoing | Completed/ Ongoing | In FY17/18, staff posted a total of 58 promos for online resources; Overdrive finished the year up 32% from FY16/17; access to ebooks continues to grow, Overdrive usage July 2018- March 2019 was 7,390 vs. July 2017-March 2018 usage of 4,808 (a 54% increase); RBdigital (formally Zinio), a digital magazine resource, has been regularly featured on the library's homepage and has seen a 17% increase in use versus the same period last year; FY18/19 saw Overdrive usage increase 55% from FY17/18 with TumbleBooks increasing 44% and RBdigital (formally Zinio) increasing 20% over the prior fiscal year; ebook usage during the Covid-19 crisis has increased 45% with 4,260 ebooks checked out Feb-Apr 2020 vs. 2930 checkouts during the same period last year; Tumblebooks, online guided ebooks for children, increased 413% and HelpNow, an online tutoring resource, increased 598% year over year (Feb-Apr 2019 vs Feb-Apr 2020); usage of HelpNow, an online tutoring resource, continues to be popular during remote learning for students, with 895 total sessions during Fiscal Year 2019/2020 (July 2019-June 2020) vs. 501 sessions during Fiscal Year 2018/2019; eBook usage was already increasing during FY19/20 and the Covid-19 crisis expanded that growth with 15,953 ebooks checked out FY 19/20 vs. 10,847 checkouts in FY18/19; TumbleBooks, online guided ebooks for children, has also seen a spike in usage during the Covid-19 crisis, with 293 sessions from March-June 2020; the state library is providing two year subscriptions to Brainfuse’s JobNow, an online career resources site, for all public libraries in California, and staff is working with Brainfuse representatives to get the site active by November to help provide yet another source of support for job seekers; usage of HelpNow from March-September totaled 1,484 sessions vs. 173 during the same time period in 2019; TumbleBooks has increased during the pandemic, with 647 sessions from March-September 2020 vs. 195 sessions from March-September 2019; JobNow/VetNow, an online resources site for job skills and veterans, was visited a total of 265 times in November & December 2020; HelpNow has increased in usage by 51% with 1,352 total sessions from July 2020-June 2021 versus 895 sessions the prior fiscal year; TumbleBooks has also seen a spike in usage with 846 sessions in FY20/21 (vs. 398 sessions during the previous fiscal year) that resulted in a 113% increase; in October 2020, the state library provided a two year subscription to Brainfuse’s updated JobNow/VetNow, an online resource site for job skills and veterans, and it has been visited a total of 1,246 times in FY20/21; other online resources continue to see increases in usage, including Overdrive ebooks with 17,762 items borrowed (up 11%) and the Legacy Project Online Collection (up 38%) from the previous fiscal year; HelpNow has had 527 sessions since school started in August 2021, with the most popular subjects being math for older students and language learning; the grant-funded book locker in Recreation Park was ordered in early October with a 3-month delivery estimate for installation in early 2022; PressReader offers options for those with technology issues, including unlimited downloads for offline viewing, a mobile app available on most major operating systems, and a text-view mode for those with slower download speeds

## SD Image
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2021
Strategic Direction: Enhance Image Strengthen the perception of the Library as a welcoming place for the community to gather
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Highlight for the community the multitude of opportunities offered by the Library | Establish a marketing team made up of 3-5 staff at various levels within the organization and create a list of the current means of promotion | Supervisors, AS & YS Staff, Circulation Staff | Q4 2017 | Q4 2018 | Completed | Members of the Marketing Team include: Rebecca, Stefanie, Victor, Julie, Josh, Erica, Linda, & Anush; meetings began September 2018 and continue monthly; reviewed current promotions and started working on ideas for a comprehensive marketing plan at the December 2018 meeting; a draft plan was reviewed by staff in December 2019 and the updated plan will be presented at the January 2020 Library Board meeting
| Create a marketing plan, consisting of 3-5 marketing strategies and work with the City's public relations staff to ensure a citywide audience | Supervisors, Marketing Team | Q4 2017 | Q4 2019 Q1 2020 | Completed | The Marketing Team completed a draft plan and met with library staff for feedback in December 2019; it will be presented at the January 2020 Library Board meeting for feedback from the board
| Expand the Library's digital presence, more effectively using the new City website and social media platforms resulting in a 10% increase in audience reach by 2020 | Supervisors, Marketing Team | Q4 2018 | Q4 2020 | Completed/ Ongoing | The Library's official Facebook page grew with a huge jump in audience reach, with the daily average for FY17/18 at 733 versus 237 in FY16/17, a 209% increase; staff is using Buffer social media scheduling software to ensure consistent and relevant content on the library's social media platforms; at the library-wide Yule Ball event in December 2018, staff asked attendees how they learned about the program and the majority of patrons cited social media posts, including several that traveled from out of town for the event; based on feedback from Youth Services programming comment cards, 39% of attendees heard about the program they were attending from online sources (social media or website); the library's Instagram account continues to grow in popularity, with 1,561 followers as of July 2020; the Marketing Team continues to collaborate virtually via the library’s Slack account to ensure updated information is shared during the library’s closure on the website and social media sites, including regular posting of virtual programming videos that resulted in a total of 7,176 views from May-June 2020; staff is actively promoting the library’s new Curbside Pickup Service with how-to videos and instructional graphics on social media, resulting in 522 items borrowed in the first week after it’s launch on July 6; is working on a promotional how-to video on the Legacy Project online historical collection to highlight the various search and browsing features available; the Instagram account has 1,662 followers as of October 2020, with the Marketing Team working on ways to maximize the platform and it's features in the most effective way possible; regular posting of virtual programming videos on the library's social media sites resulted in a total of 6,121 views in August and September 2020; library content on Facebook and Instagram resulted in a total of 8,085 post views in November and December 2020, with 1,723 followers on the library's Instagram account; staff have created a number of promotional how-to videos on topics such as the Legacy Project online historical collection, JobNow/VetNow, the library catalog, and HelpNow to highlight the various resources and features available for patrons with a total of 2,518 views (as of January 6); library posts on Facebook and Instagram reached 15,369 accounts in the first three months of 2021; the library’s Facebook account has 1,085 followers and the Instagram account has 1,828 followers; staff reviewed and updated elements of the library’s website to help optimize searching and make it easier for community members to find information about library resources and programs; as of July 2021, the library’s Facebook account has 1,110 followers and the Instagram account has 1,895 followers, with the library’s new YouTube channel, that launched May 3rd, having a total of 44 subscribers as of June 30; a total of 17,978 accounts were reached on the library’s Facebook and Instagram accounts in the first six months of 2021 (11,512-IG & 6,466-FB); short videos promoting book suggestions on Instagram have been particularly popular, with the two videos posted in September 2021 having a total of 550 views; staff and a VRC volunteer was interviewed by ABC 7 in October for a segment that promotes the services and resources offered by the Veterans Resource Center, with a link to the segment shared on our social media sites
| Explore use of patron comment cards and targeted surveys and launch for use by 2018 at 25% of programs | YS Staff, Supervisors | Q2 2017 | Q2 2018 | Completed | YS Staff introduced survey cards for programs in Q2 2017; paper or verbal survey questions were used at 30% of programs as of December 2017; Adult Services Staff started using program surveys in Spring 2018; the Book to Action grant programs of April and May 2021 had a total of 25 survey responses as of June 2021
Goal 2: Partner with the City Facility Staff to identify annual maintenance needs | Meet with facility staff and assess needs on a quarterly basis | Library Manager, Circulation Supervisor | Q2 2018 | ongoing | Completed/ Ongoing | Library staff meet regularly with Facility staff; created facility checklist January 2017; Public Works Staff in charge of the facility are a regular presence and respond promptly to building issues
| Create maintenance needs plan and revisit on a quarterly basis | Supervisors | Q3 2018 | ongoing | Completed/ Ongoing | Created facility checklist January 2017; worked with PW Staff on facility needs related to the building's ten year anniversary in 2019; updated facility needs list for PW Staff in December 2019; staff continue to work with PW Staff on facility needs, particularly the specialized needs to reopen the library building to ensure health and safety standards set by the state and county are met
Goal 3: Better engage with the following key stakeholder groups - City staff, religious groups, and area service organizations | Continue building Library Express program for City staff, resulting in a library card holder rate among City staff of 90% by 2020 | Library Express Team | Q4 2017 | Q4 2020 | Completed/ Ongoing | Library Express Team, as of 2018: Miga & Julie; introduced new library card design during National Library Card Signup Month September 2017 & encouraged signups by offering free replacement cards; City's new on-boarding process includes a stop at the library to sign up new employees for cards; for National Library Card Signup Month in September 2018, 73 city staff received cards due to outreach efforts by staff; thanks to the work of the Library Express Team and the new on-boarding process, all full-time employees have library cards
| Promote Summer Reading Program to City staff, resulting in a program registration rate among City staff of 50% by 2019 | Library Express Team | Q3 2017 | Q4 2019 | Completed/ Ongoing | Library Express Team signed up 68 City staff during Summer Reading 2017 and expanded their promotion for Summer Reading 2018, with a program registration rate of 40%; staff did a wonderful job engaging City staff for Summer Reading 2019 and signed up 96 staff members, a 56% registration rate
| Staff will regularly attend Healing Connections meetings and establish at least one program or partnership collaboration with a Healing Connections member by 2021 | Library Manager, YS Supervisor | Q3 2017 | Q3 2021 | Completed | Staff attended the 2017 & 2018 Strategic Plan Meetings for the organization; Partnered with HC for March 4 Balance programs in March 2018, Talking With Your Teen and Express Yourself Through Art with a total attendance of 48 teens and parents at the two programs; continue to attend the monthly meetings when available; held a March 4 Balance program, Express Yourself Through Art, for teens in 2019 and will continue M4B programs moving forward
| Staff will explore partnership opportunities with Foothill Unity and the Interfaith Council by establishing a partnership agreement and/or collaborating on a program or service by 2021 | AS Supervisor | Q2 2018 | Q2 2021 | Completed/ Ongoing | Staff provided library services at the Foothill Unity Back to School Event in August 2018 and returned for the 2019 event, reaching 150 people; staff toured the Foothill Unity Center in February 2019 and discussed ways to bring early literacy and veterans services to the center during distribution days; VRC volunteers and staff participated in the Foothill Unity Health Fair in March 2019 to highlight services available for veterans at the library, speaking with 170 attendees; Veterans Resource Center staff and volunteers participated in the City’s summer concerts in July & August 2019 to promote veterans resources to the larger community; Veterans Resource Center staff and volunteers were awarded a certificate of recognition for service to veterans from State Senator Portantino in November 2019 as well as the Monrovia Chamber of Commerce’s annual Military Service & Stewardship Award in January 2020 for their positive impact on the lives of local veterans and their families

## SD Staff
City of Monrovia - Monrovia Public Library Strategic Plan - SMART Goals 2017-2022 UPDATED OCTOBER 2021
Strategic Direction: Enhance Staff Development Develop ways to invest in our team to be their best in the delivery of programs and services to our community
SMART Goal | Supporting Activities | Responsible Staff | Start Date | Due Date | Status | Notes
Goal 1: Engage staff in the Strategic Planning process and Organizational Values | Clearly outline for all staff the organizational values as well as the Library Strategic Directions and SMART Goals with regular updates and discussions at monthly staff and departmental meetings by 2018 | Supervisors | Q2 2017 | Q1 2018 ongoing | Completed/ Ongoing | Part of agendas for monthly staff and departmental meetings; held small-scale and individual meetings with staff in February 2019 to review the progress of the plan and discuss ideas for the future; as part of the Marketing Plan draft review, met with staff in small-scale meetings in December 2019 to solicit feedback and discuss how the plan will guide library marketing and promotion moving forward
| Align professional development opportunities with organizational values and strategic directions, incorporating these elements into staff's annual evaluations by 2019 | Supervisors | Q2 2017 | Q1 2019 | Completed | Supervisors worked with Staff to develop individual evaluation goals that align and support the strategic plan to be included in their annual evaluations
Goal 2: Develop ways to celebrate the success and contributions of staff and volunteers | Work with Human Resources regarding new evaluation process to provide timely and meaningful feedback to staff within 60 days of their anniversary date by 2018 | Supervisors | Q3 2017 | Q1 2018 | Completed | City updated evaluation process for Part-Time employees December 2017; a new online evaluation software, CityGrows, was launched in January 2019, streamling the process while ensuring annual evaluations continue to celebrate achievements and continuous improvement
| Work with the Volunteer Management Team (VMT) on volunteer feedback opportunities and methods, including creating a comment card and regular review of volunteer survey data that will result in positive volunteer testimonials and a higher retention rate than FY16/17 | AS Supervisor, Volunteer Team | Q4 2017 | ongoing | Completed | A comment card created for volunteers was launched in January 2018; the Volunteer Team provided training for volunteers on handling difficult situations in June 2018 and provides ongoing training for new volunteers; these positive changes have resulted in higher retention rates for volunteers than in the past
| Work with the VMT to plan 2-4 Volunteer Celebrations each year | AS & YS Supervisors, AS Librarian, & Teen Librarian | Q3 2017 | ongoing | Completed/ Ongoing | In 2017, 4 events were held: Volunteer Celebration February 2017, TAB Recognition June 2017, Volunteer Celebration September 2017, and Literacy Holiday Potluck December 2017; in 2018, 2019, a Volunteer Celebration was held in March 2018 and Teen Volunteer Recognition in August 2018; the Volunteer Celebration in February 2019 was attended by 38 volunteers and the Teen Volunteer Recognition party was held in August 2019 with 34 teens; the next Volunteer Celebration is planned for May 2020
Goal 3: Support regular and ongoing professional development for staff | Create professional development plan that includes meaningful outcomes and goals for library departments | BELC Team | Q2 2017 | Q4 2017 | Completed | 2017 BELC Team includes: Annette, Victor, Dan, Julie, Rebecca, Elizabeth, Carey; Created Professional Development Plan April 2017 that includes both library-wide and department goals
| Schedule 100% of staff for regular professional development time, at least three hours per month and maintain "Learning Hour" logs so newly acquired skills and knowledge can be included in yearly evaluations by 2019 | Supervisors | Q2 2017 | Q1 2019 | Completed/ Ongoing | Learning Hours for all staff were introduced in early Spring 2017; Each staff member has 3-4 Learning Hours scheduled per month; staff have used the Learning Hours to do the following: learn Spanish, expand their Excel skills, review library databases, learn sign language (ASL), participate in library-wide training webinars such as Ryan Dowd's Homelessness in Libraries series; staff continue to use Learning Hours while working from home, learning about a variety of topics, including - Excel, sign language, basic Spanish, safety procedures, homelessness, mental health, virtual services, customer service, racial justice, program evaluation, and collection development; each staff member has completed the National Incident Management System (NIMS) and Standardized Emergency Management System (SEMS) trainings over the past few months; these two trainings require 8-12 hours per staff member and are integral to responding effectively in an emergency situation; staff completed the City’s annual customer service, sexual harassment, and driver safety trainings via the California JPIA’s online training portal
| Establish annual in-house professional development workshop for staff | Staff Learning Summit Planning Team | Q2 2017 | Q3 2017 | Completed/ Ongoing | Staff Learning Summit was held August 11, 2017 with presentations on Canva, learning hours, and readers advisory as well as lots of positive feedback from staff surveys after the event; the 2nd Annual Staff Learning Summit was held on August 9, 2018 with presentations on safety, Tinkercad, customer service, and library history; post-summit surveys from staff were very positive; the third annual staff summit on August 8, 2019 had presentations by staff on local history resources, journal making, library advocacy, mental health and wellbeing, and programming; after three staff summits, all staff have had the opportuntiy to present and look forward to the 2020 Staff Learning Summit; a new program, Collab Lab, launched in early 2020, and is continuing with virtual meetings among the staff teams; each Collab Lab team is collaborating on grant research and virtual programming while working remotely; the Collab Lab team working on grants was able to secure a $42,580 LSTA Grant from the state for a remote locker in Recreation Park; staff participated in the mandatory First Aid/CPR training held by the City in August & September 2021, this training is held every 2 years
| 2021 SP EXPANSION ITEM: Work with Human Resources and other professional development resources to ensure 100% of staff participate on a regular basis in training that focuses on providing inclusive services | Supervisors | Q3 2021 | Q4 2022 | Completed/ Ongoing | All staff attended City trainings on overcoming unconscious bias, anti-bullying, and creating a respectful workplace in June 2020; Literacy staff participated in webinars on providing services to those with Dsylexia in March 2021